## Sheet1
Date | Form | Task | Date Task Completed
18/06/23 | Login form | Set tab order | 18/06/23
19/06/23 | Add User form | Check to ensure that password and confirm password should match | 30/06/23
19/06/23 | Add User form | When add is clicked, set focus of the cursor to full name field | 30/06/23
19/06/23 | Add user form | Encrypted field should not be shown on the password field | 30/06/23
19/06/23 | Add user form | Add code to save button | 30/06/23
19/06/23 | Add user form | Add code to cancel button | 30/06/23
19/06/23 | Login form | Close form when OK button is clicked and login is successful | 30/06/23
30/06/23 | Add user form | Add code to delete btn | 30/06/23
30/06/23 | Add user form | Data for access field is not saved when the option is selected by pressing the first letter of the option on the keyboard and not by selecting using the mouse or touchpad of the laptop | 30/06/23
2023-02-07 | Login form | Set opacity
2023-02-07 | Inventory form | Tab order | 2023-02-07
2023-02-07 | Inventory form | When add is clicked, set focus to asset name field | 2023-02-07
2023-02-07 | Inventory form | see lesson on udemy to add items to all comboboxes
2023-02-07 | Inventory form | Add code to Save btn
2023-02-07 | Inventory form | Add code to Cancel btn
2023-02-07 | Inventory form | Add code to Delete btn
2023-02-07 | Inventory form | Fix Edited by
2023-02-07 | Inventory form | Fix time stamp
17/07/2023 | Inventory form | How to make date fields blank on adding new records
17/07/2023 | Main form | Add necessary features to it
20/07/2023 | Inventory form | recent items added in the combo item form is not updated in the specific combobox in the inventory form | 26/07/23
21/07/2023 | Inventory form | Empty date in the dgv is not shown as empty in the dtp | 27/07/23
25/08/2023 | Add User form | grid data is not shown on controls esp textboxes | 25/08/23
25/08/2023 | Add User form | password displayed on the control should not show the characters | 2023-05-09
2023-05-09 | Inventory form | Change control asset name field from textbox to combobox
2023-05-09 | Inventory form | Change control brand field from textbox to combobox
2023-05-09 | Inventory form | Change control category field from textbox to combobox